**Project Scope Statement**

**Project object:**

To organise and lead a five-day fly-fishing expedition down the Tikchik River System in Alaska from 21 to 25 June at cost no more than US$50,000.

**Deliverable:**

1. Provide air transportation from Dillingham, Alaska to Camp I and from Camp II back to Dillingham.
2. Provide rive transportation consisting of two eight-man drift boats with outboard motors.
3. Provide three meals a day for five days spent on the river.
4. Provide fly-fishing instruction / training
5. Provide overnight accommodations at Dillingham lodge plus three four-man tents with beddings and lanterns.
6. Provide four experienced river guides who are also fly fisherman.
7. Provide finishing licenses for all guests

**Milestones:**

1. Contract signed on 22 February
2. Guests arrive in Dillingham at 20 June
3. Depart by plane to Camp I on 21 June
4. Depart by plane from Camp II to Dillingham on 25 June

**Technical requirements:**

1. Air transportation to and from camps
2. Boat transportation within the Tikchik River system
3. Digital mobile communication devices
4. Camps and fishing conform to state of Alaska requirements

**Limits and exclusions:**

1. Guests are responsible for travel arrangements to and from Dillingham, Alaska
2. Guests are responsible for their own fly-fishing equipment and clothing.
3. Local air transportation to and from base camps will be outsourced
4. Tour guides are not responsible for the number of king salmon caught by guests.

**Customer review:**

The president of Blue Note (which is the client)