## Sheet1
Q1
ID | Project | 2019 | 2020 | 2021 | 2022 | 2023 | Benefits
1 | HQ | 2 | 2 | 5 | 3 | 3 | 50
2 | Factory | 10 | 10 | 8 | 10 | 10 | 60
3 | Logo | 20 | 20 | 10 |  |  | 70
4 | IT |  |  | 8 | 8 | 8 | 60
5 | Warehouse | 10 | 15 |  |  |  | 75
6 | Staff | 1.5 |  | 1.5 |  | 1.5 | 5
7 | Office |  | 20 |  | 20 |  | 50
8 | Canteen |  | 2.5 | 2.5 |  | 2.5 | 35
9 | Electrical | 15 |  | 17 |  | 20 | 65
10 | Elevator | 18 | 20 |  | 17 |  | 60
11 | Tricks | 7 | 3 |  |  |  | 40
12 | Rails |  |  |  | 4 |  | 23
| Annual Budget | 30 | 25 | 25 | 25 | 25
Step 1: Defind decision variables
x_1: if we select project_i, x_i = 1; if we don't select project_i, x_i=0. (i=1, ,2, 3, 4 …, 12)
Step 2: Define objective function
Objective: Maximum total benefits
Max Z = 50*x_1 + 60*x_2 + 70*x_3 + 60*x_4 + 75*x_5 + 5*x_6 + 50*x_7 + 35*x_8 + 65*x_9 + 60*x_10 + 40*x_11 + 23*x_12
Step3: Define constraints
1st type of constraints: Annual badget
2019: | 2*x_1 + 10*x_2 + 20*x_3 + 10*x_5 + 1.5*x_6 + 15*x_9 + 18*x_10 + 7*x_11 <= 30 | [6 empty] | (COn1)
2020: | 2*x_1 + 10*x_2 + 20*x_3 + 15*x_5 + 20*x_7 + 2.5*x_8 + 20*x_10 + 3*x+11 <=25 | [6 empty] | (Con2)
2021: | 5*x_1 + 8*x_2 + 10*x_3 + 8*x_4 + 1.5*x_6 + 2.5*x_8 + 17*x_9 <=25 | [6 empty] | (Con3)
2022: | 3*x_1 + 10*x_2 + 8*x_4 + 20*x_7 + 17*x_10 + 4*x_12 <= 25 | [6 empty] | (Con4)
2023: | 3*x_1 + 10*x_2 + 8*x_4 + 1.5*x_6 + 2.5*x_8 + 20*x_9 <= 25 | [6 empty] | (Con5)
2nd type of constraints: Dependency between projects
1. Project 1 must be selected with project 4.
We either select project 1 and 4 together (x_1=1, x_4=1) or we deselect them together (x_1 = 0, x_4 =0)
x_1 = x_4 |  | (Con7)
2. Project 2 cannot be selected with project 7.
When we select project 2 (x_2 =1), we can't select project 7 (x_7=0)
When we select project 7 (x_7 =1), we can't select project 2 (x_2=0)
When we deselect project 2 (x_2=0), prject 7 can be selected or deselected (x_7 = 1 or 0).
When we deselect project 7 (x_7=0), prject 2 can be selected or deselected (x_2 = 1 or 0).
x_2 + x_7 <=1 |  | (Con8)
3. Project 9 can only be selected if project 5 is selected.
When we select project 5 (x_5 = 1), we can select or deselect project 9 (x_9 = 1 or 0)
When we deselect project 5 (x_5 = 0), we cannot select project 9 (x_9 = 0)
x_5 >= x_9 |  | (Con9)
4. The firm must select one of either project 11 and 12, but not both.
When we select project 11 (x_11 = 1), we cannot select 12 (x_12 = 0)
When we select project 12 (x_12 = 1), we cannot select 11 (x_!1 = 0)
We cannot deselct project 11 and 12 at the same time.
x_11 + x_12 =1 |  | (Con10)

## Sheet2
Q2
ID | Description | Predecessor | Time (days) | Cost
A | System designs | None | 2 | 1000
B | Subsystem A design | A | 1 | 500 | ES |  | EF
C | Subsystem B design | A | 1 | 500 | Slack | Desc
D | Subsystem C design | A | 1 | 500 | LS | Dur. | LF
E | Program A | B | 2 | 1000
F | Program B | C | 10 | 5000
G | Program C | D | 2 | 1000
H | Subsystem A test | E | 1 | 500
I | Subsystem B test | F | 1 | 500
J | Subsystem C test | G | 1 | 500
K | Integration | H,I,J | 2 | 1000
L | Final test | K | 1 | 500
[5 empty] | Total Slack: | 1 |  | Total Slack: |  |  | Total Slack:
[5 empty] | 2 | B | 3 | 3 | E | 5 | 5 | H | 6
[5 empty] | 8 | Subsystem A design |  | 8 | Program A |  | 8 | Subsystem A test
[5 empty] | 10 | 1 | 11 | 11 | 2 | 13 | 13 | 1 | 14
|  | 0 | A | 2
|  | 0 | System designs |  | 2 | C | 3 | 3 | F | 13 | 13 | I | 14 | 14 | K | 16 | 16 | L | 17
|  | 0 | 2 | 2 | 0 | Subsystem B design |  | 0 | Program B |  | 0 | Subsystem B test |  | 0 | Integration |  | 0 | Final test
[5 empty] | 2 | 1 | 3 | 3 | 10 | 13 | 13 | 1 | 14 | 14 | 2 | 16 | 16 | 1 | 17
[5 empty] | 2 | D | 3 | 3 | G | 5 | 5 | J | 6
[5 empty] | 8 | Subsystem C design |  | 8 | Program C |  | 8 | Subsystem C test
[5 empty] | 10 | 1 | 11 | 11 | 2 | 13 | 13 | 1 | 14
ES + Duration = EF
LF - Duration = LS
Total Slack = LS - ES ( or LF - EF)
Free Slack = ES of the next immediate node) minus (EF of the current node)
(a) The project will take 16 days.
(b)
Critical activities: A, C, F, I, K
Critical path: A - C -F -I -K