## Q1
Total slcak = LS - ES = LF - LS
Free slack = ES of next node - EF of current node
AON model
| ES | Code | EF
| TS | Activity Name
| LS | Duration | LF |  | 2 | B | 3 |  | 3 | E | 5 | 5 | H | 6
[5 empty] | 8 | Subsystem A design |  |  | 8 | Program A |  | 8 | Subsystem A test
[5 empty] | 10 | 1 | 11 |  | 11 | 2 | 13 | 13 | 1 | 14
[6 empty] | FS | 0 |  |  | FS | 0 |  | FS | 8
| 0 | A | 2 |  | 2 | C | 3 |  | 3 | F | 13 | 13 | I | 14 | 14 | K | 16 | 16 | L | 17
| 0 | System designs |  |  | 0 | Subsystem B design |  |  | 0 | Program B |  | 0 | Subsystem B test |  | 0 | Integration |  | 0 | Final test
| 0 | 2 | 2 |  | 2 | 1 | 3 |  | 3 | 10 | 13 | 13 | 1 | 14 | 14 | 2 | 16 | 16 | 1 | 17
[5 empty] | 2 | D | 3 |  | 3 | G | 5 | 5 | J | 6
[5 empty] | 8 | Subsystem C design |  |  | 8 | Program C |  | 8 | Subsystem C test
[5 empty] | 10 | 1 | 11 |  | 11 | 2 | 13 | 13 | 1 | 14
[6 empty] | FS | 0 |  |  | FS | 0 |  | FS | 8
| ID | Description | Predecessor | Time (days) | Cost
| A | System designs | None | 2 | 1000 |  | a) It will take 17 days for the project to finish
| B | Subsystem A design | A | 1 | 500 |  | b)
| C | Subsystem B design | A | 1 | 500 |  | Non-critical activity | TS | FS
| D | Subsystem C design | A | 1 | 500 |  | B | 8 | 0
| E | Program A | B | 2 | 1000 |  | D | 8 | 0
| F | Program B | C | 10 | 5000 |  | E | 8 | 0
| G | Program C | D | 2 | 1000 |  | G | 8 | 0
| H | Subsystem A test | E | 1 | 500 |  | H | 8 | 8
| I | Subsystem B test | F | 1 | 500 |  | J | 8 | 8
| J | Subsystem C test | G | 1 | 500
| K | Integration | H,I,J | 2 | 1000
| L | Final test | K | 1 | 500

## Q2
ID | Description |  | Predecessor | Time (days) | Cost
A | System designs |  | None | 2 | 1000
B | Subsystem A design |  | A | 1 | 500
C | Subsystem B design |  | A | 1 | 500
D | Subsystem C design |  | A | 1 | 500
E | Program A |  | B | 2 | 1000
F | Program B |  | C | 10 | 5000
G | Program C |  | D | 2 | 1000
H | Subsystem A test |  | E | 1 | 500
I | Subsystem B test |  | F | 1 | 500
J | Subsystem C test |  | G | 1 | 500
K | Integration |  | H,I,J | 2 | 1000
L | Final test |  | K | 1 | 500
Conver AON (Activity on node) to AOA (Activity on arc)
E
[5 empty] | 2 |  | 5
|  |  |  | B |  |  |  | H
|  | A |  | C |  | F |  | I |  | K |  | L
| 0 |  | 1 |  | 3 |  | 6 |  | 8 |  | 9 |  | 10
J
|  |  |  | D |  | G
[5 empty] | 4 |  | 7
| variable | x_i (i=1,2,3,,…,10)(x_i is non-negative
| Objective | Minimize x_10
(Minimize the project duration)
Constraints:
[5 empty] | x_0 | x_1 | x_2 | x_3 | x_4 | x_5 | x_6 | x_7 | x_8 | x_9 | x_10
|  |  |  | Variables | 0 | 2 | 11 | 3 | 3 | 13 | 13 | 13 | 14 | 16 | 17
|  |  |  | Objective | [13 empty] | 17 | bar: x_10
Constraints
|  |  |  | x_1 - x_0 >=2 | [11 empty] | >= | 2 | 2 | bar: x_0 to x_1
|  |  |  | x_2 - x_2 >=1 | [11 empty] | >= | 1 | 9 | bar: x_1 to x_2
|  |  |  | x_3 - x_1 >=1 | [11 empty] | >= | 1 | 1 | bar: x_1; x_3
|  |  |  | x_4 - x_1 >=1 | [11 empty] | >= | 1 | 1 | bar: x_1; x_4
|  |  |  | x_5 - x_2 >=2 | [11 empty] | >= | 2 | 2 | bar: x_2; x_5
|  |  |  | x_6 - x_3 >=10 | [11 empty] | >= | 10 | 10 | bar: x_3; x_6
|  |  |  | x_7 - x_4 >=2 | [11 empty] | >= | 2 | 10 | bar: x_4; x_7
|  |  |  | x_8 - x_5 >=1 | [11 empty] | >= | 1 | 1 | bar: x_5; x_8
|  |  |  | x_8 - x_6 >=1 | [11 empty] | >= | 1 | 1 | bar: x_6; x_8
|  |  |  | x_8 - x_7 >=1 | [11 empty] | >= | 1 | 1 | bar: x_7 to x_8
|  |  |  | x_9 - x_8 >= 2 | [11 empty] | >= | 2 | 2 | bar: x_8 to x_9
|  |  |  | x_10 - x_9 >=1 | [11 empty] | >= | 1 | 1 | bar: x_9 to x_10

## Q3
Calculate he slope of eac activity
= (Crashing cost - Normal cost) / Allowable decrease
Activity | Duration | Predecessor(s) | Normal Cost | Allowable Decrease | Crashing Cost |  | Activity | Normal Cost | Allowable Decrease | Crashing Cost | Slope
A | 2 | None | 20 | 0 | 20 |  | A | 20 | 0 | 20 | n/a | the allowable decrease = 0, we cannot crash activity A
B | 3 | A | 35 | 1 | 40 |  | B | 35 | 1 | 40 | 5
C | 5 | B | 35 | 2 | 51 |  | C | 35 | 2 | 51 | 8
D | 7 | A | 50 | 2 | 66 |  | D | 50 | 2 | 66 | 8
E | 6 | A+FS1 | 30 | 1 | 36 |  | E | 30 | 1 | 36 | 6
F | 2 | C, D | 10 | 1 | 20 |  | F | 10 | 1 | 20 | 10
G | 2 | E, F | 10 | 1 | 30 |  | G | 10 | 1 | 30 | 20
[7 empty] | Indirect cost | 15 | per week
Step 0: Draw project network and find critical path
|  | B |  | C |  |  |  | Path | Duration
|  | 3 |  | 5 |  |  |  | AEG | 11
[8 empty] | ABCFG | 14 | Critical path
[8 empty] | ADFG | 13
A |  | D |  | F |  | G
2 |  | 7 |  | 2 |  | 2 |  | Duration | Direct cost | Indirect cost | Total cost
[8 empty] | 14 | 190 | 210 | 400
Direct cost = sum of normal cost
|  | E | [5 empty] | Indirect cost = duration * indirect cost per week
6
Step 1: Reduce Activity B for one week ( because B has the smallest slope and the allowable decrease of B is 1)
|  | B |  | C
|  | 2 |  | 5
(x)
A |  | D |  | F |  | G |  | Path | Duration
2 |  | 7 |  | 2 |  | 2 |  | AEG | 11
[8 empty] | ABCFG | 13 | Critical path
[8 empty] | ADFG | 13 | Critical path
E
|  | 6 |  |  |  |  | Duration | Direct cost | Indirect cost | Total cost
[7 empty] | 13 | 195 | 195 | 390
Direct cost = sum of normal cost + crashing cost of B
Step 2: Reduce activity F for one week
Three options: |  |  | Cost
1. Crash C &D at the same time |  |  | 16
2. Crash F individually |  |  | 10
3. Crash G individually |  |  | 20
|  | B |  | C
|  | 2 |  | 5
(x)
A |  | D |  | F |  | G |  | Path | Duration
2 |  | 7 |  | 1 |  | 2 |  | AEG | 11
[8 empty] | ABCFG | 12 | Critical path
[8 empty] | ADFG | 12 | Critical path
E
|  | 6 |  |  |  |  | Duration | Direct cost | Indirect cost | Total cost
[7 empty] | 12 | 205 | 180 | 385
Step 3: Reduct C and D for one week
Two options: |  |  | Cost
1. Crash C &D at the same time |  |  | 16
2. Crash G individually |  |  | 20
|  | B |  | C
|  | 2 |  | 4 | crash for 1 week
(x)
A |  | D |  | F |  | G |  | Path | Duration
2 |  | 5 |  | 1 |  | 2 |  | AEG | 11 | Critical path
[8 empty] | ABCFG | 11 | Critical path
[8 empty] | ADFG | 11 | Critical path
E
|  | 6 |  |  |  |  | Duration | Direct cost | Indirect cost | Total cost
|  | crash for 1 week |  |  |  |  | 11 | 221 | 165 | 386
Step 4: Reduct G for one week
Two options: |  |  | Cost
1. Crash C, D & E at the same time |  |  | 22 | crashing C&D doesn't change the duration, therefore crashing3 activities because we wanna change the duration
2. Crash G individually |  |  | 20
|  | B |  | C
|  | 2 |  | 4 | crash for 1 week
(x)
A |  | D |  | F |  | G |  | Path | Duration
2 |  | 5 |  | 1 |  | 2 |  | AEG | 10 | Critical path
[8 empty] | ABCFG | 10 | Critical path
[8 empty] | ADFG | 10 | Critical path
E
|  | 6 |  |  |  |  | Duration | Direct cost | Indirect cost | Total cost
|  | crash for 1 week |  |  |  |  | 10 | 241 | 150 | 391
Step 4: Reduct G for one week
One options: |  |  | Cost
1. Crash C, D & E at the same time |  |  | 22 | crashing C&D doesn't change the duration, therefore crashing3 activities because we wanna change the duration
|  | B |  | C
|  | 2 |  | 4 | crash for 1 week
(x)
A |  | D |  | F |  | G |  | Path | Duration
2 |  | 5 |  | 1 |  | 2 |  | AEG | 9 | Critical path
[8 empty] | ABCFG | 9 | Critical path
[8 empty] | ADFG | 9 | Critical path
E
|  | 6 |  |  |  |  | Duration | Direct cost | Indirect cost | Total cost
|  | crash for 1 week |  |  |  |  | 9 | 263 | 135 | 398
Summary
| Duration | Direct cost | Indirect cost | Total cost
| 14 | 190 | 210 | 400
| 13 | 195 | 195 | 390
| 12 | 205 | 180 | 385
| 11 | 221 | 165 | 386
| 10 | 241 | 150 | 391
| 9 | 263 | 135 | 398
Part 2
| Activity | Normal Cost | Allowable Decrease | Crashing Cost | Slope
| A | 20 | 1 | 25 | 5
| B | 35 | 1 | 40 | 5
| C | 35 | 2 | 51 | 8
| D | 50 | 2 | 66 | 8
| E | 30 | 1 | 36 | 6
| F | 10 | 1 | 20 | 10
| G | 10 | 1 | 30 | 20
Summary
Activity to crash | Duration | Direct cost | Indirect cost | Total cost
| 14 | 190 | 210 | 400
B | 13 | 195 | 195 | 390
A | 12 | 200 | 180 | 380
F | 11 | 210 | 165 | 375 | optimal
C & D | 10 | 226 | 150 | 376
G | 9 | 246 | 90 | 391
C & D &G | 8 | 268 | 72 | 340
Duration for the project will change to 11 weeks.
Q4
Time-constrained: the objective is to minimize time
Resources-constrained: the objective is to minimize resourses