## Q1a
Q1a
| ES | Code | EF
| TS | Activity Name
| LS | Duration | LF |  |  |  | 10 | G | 16
[7 empty] | 4 | Documentation
|  |  |  | 3 | B | 10 | 14 | 6 | 20 | 16 | H | 18
|  |  |  | 4 | Marketing assessment |  |  |  |  | 4 | Pricing
|  |  |  | 7 | 7 | 14 |  |  |  | 20 | 2 | 22
| 0 | A | 3
| 0 | Requirement |  |  |  |  | 9 | D | 16 |  |  |  | 22 | I | 26 | 26 | J | 29
| 0 | 3 | 3 |  |  |  | 1 | Development |  |  |  |  | 0 | Production |  | 0 | Distribtuion
[7 empty] | 10 | 7 | 17 |  |  |  | 22 | 4 | 26 | 26 | 3 | 29
|  |  |  | 3 | C | 9 |  |  |  | 17 | F | 22
|  |  |  | 0 | Design |  |  |  |  | 0 | Revising
|  |  |  | 3 | 6 | 9 |  |  |  | 17 | 5 | 22
[7 empty] | 9 | E | 17
[7 empty] | 0 | Testing
[7 empty] | 9 | 8 | 17
| Task | Normal Cost ($000)
| A | 10
| B | 20
| C | 15
| D | 45
| E | 10
| F | 15
| G | 20
| H | 10
| I | 5
| J | 35
| Total cost | 185
Q1a)
What is the estimated completion time for the project?
Under the "Normal" circustance, the estimated completion time for the project is 29 weeks.
What is the estimated project budget?
The estimated project budget is $185,000.
What is the probability that the project can be completed in 28 week?

## Q1b
Q1b
| Task | Normal Cost ($000) | Crash cost ($000) | Allowable decrease (Week) | Slope
| A | 10 | 10 | 0 | n/a
| B | 20 | 25 | 1 | 500%
| C | 15 | 30 | 1 | 1500%
| D | 45 | 50 | 1 | 500%
| E | 10 | 16 | 1 | 600%
| F | 15 | 18 | 1 | 300%
| G | 20 | 30 | 2 | 500%
| H | 10 | 15 | 1 | 500%
| I | 5 | 5 | 0 | n/a
| J | 35 | 55 | 1 | 2000%
Step 0: Draw project network and find critical path
[6 empty] | G | H |  |  | Path | Duration
[6 empty] | 6 | 2 |  |  | ABGHIJ | 25
|  |  |  | B | [5 empty] | ACDFIJ | 28
|  |  |  | 7 | [5 empty] | ACEFIJ | 29 | Critical path
|  | A | [5 empty] | I | J | Duration | Cost
|  | 3 |  |  |  | D |  | 4 | 3 | 29 | 215
|  |  |  | C |  | 7 | F
|  |  |  | 6 |  |  | 5
E
8
Step 1: Reduce task F for one week (because F has the smallest slope )
Cost
| Crash F | 18
[6 empty] | G | H |  |  | Path | Duration
[6 empty] | 6 | 2 |  |  | ABGHIJ | 25
|  |  |  | B | [5 empty] | ACDFIJ | 27
|  |  |  | 7 | [5 empty] | ACEFIJ | 28 | Critical path
|  | A | [5 empty] | I | J | Duration | Cost
|  | 3 |  |  |  | D |  | 4 | 3 | 28 | 203
|  |  |  | C |  | 7 | F
|  |  |  | 6 |  |  | 4
[6 empty] | E | (x)
8
Step 2: Crash task E for one week
| 3 options: | Cost
| 1. Crash C | 30
| 2. Crash E | 16 |  |  |  | G | H |  |  | Path | Duration
| 3. Crash J | 55 |  |  |  | 6 | 2 |  |  | ABGHIJ | 25
|  |  |  | B | [5 empty] | ACDFIJ | 27 | Critical path
|  |  |  | 7 | [5 empty] | ACEFIJ | 27 | Critical path
|  | A | [5 empty] | I | J | Duration | Cost
|  | 3 |  |  |  | D |  | 4 | 3 | 27 | 219
|  |  |  | C |  | 7 | F
|  |  |  | 6 |  |  | 4
E
7
(x)
Step 3: Crash task C for one week
| 2 options: | Cost
| 1. Crash C | 30
| 2. Crash J | 55 |  |  |  | G | H |  |  | Path | Duration
[6 empty] | 6 | 2 |  |  | ABGHIJ | 25
|  |  |  | B | [5 empty] | ACDFIJ | 26 | Critical path
|  |  |  | 7 | [5 empty] | ACEFIJ | 26 | Critical path
|  | A | [5 empty] | I | J | Duration | Cost
|  | 3 |  |  |  | D |  | 4 | 3 | 26 | 249
|  |  |  | C |  | 7 | F
|  |  |  | 5 |  |  | 4
|  |  |  | (x) |  | E
7
Step 4: Crash task J for one week
Cost
| 1. Crash J | 55
[6 empty] | G | H |  |  | Path | Duration
[6 empty] | 6 | 2 |  |  | ABGHIJ | 24
|  |  |  | B | [5 empty] | ACDFIJ | 25 | Critical path
|  |  |  | 7 | [5 empty] | ACEFIJ | 25 | Critical path
|  | A | [5 empty] | I | J | Duration | Cost
|  | 3 |  |  |  | D |  | 4 | 2 | 25 | 304
|  |  |  | C |  | 7 | F
|  |  |  | 5 |  |  | 4
E
7
Crashing summary
| Task to crash | Duration | Cost
|  | 29 | 215
| F | 28 | 203 | optimal
| E | 27 | 219
| C | 26 | 249
| J | 25 | 304
Q1b)
Which tasks do you recommend for crashing?
The optimal crashing plan is to crash task F for one week. The duration of the project will be reduced to 28 weeks and the toal cost is $203,000.
What is the probability of completing the project in 28 weeks?

## Q2
Q2a
| Year | Project A | Project B
| 0 | -500 | -500
| 1 | 400 | 300
| 2 | 300 | 350
| 3 | n/a | 80
| IRR | 27.18% | 25.77%
Q2b | Discount Rate | 8%
NPV = Initial investment + NPV(Discount rate, cells of future cash flow)
|  | Project A | Project B
| NPV | 127.572 | 141.3529
Q2c |  | Duration
| Project A | 2 | years
| Project B | 3 | years
| Minimum common multiplier |  | 6
| Year | Project A |  |  | Project B
|  | Inflow | Outflow | Cummulative cash flow | Inflow | Outflow | Cummulative cash flow
| 0 |  | -500 |  |  | -500
| 1 | 400 |  | 400 | 300 |  | 300
| 2 | 300 | -500 | -200 | 350 |  | 350
| 3 | 400 |  | 400 | 80 | -500 | -420
| 4 | 300 | -500 | -200 | 300 |  | 300
| 5 | 400 |  | 400 | 350 |  | 350
| 6 | 300 |  | 300 | 80 |  | 80
|  |  | adjusted NPV | 330.7137 |  | adjusted NPV | 253.5635
| Discount Rate | 8%
NPV = Initial investment + NPV(Discount rate, cells of future cash flow)
Q2a) The IRR for project A is 27.2% while the IRR for project B is 25.8%.
Q2b) Without considering unequal project duration, the NPV for project A is 127.6 while the NPV project B is 141.4. With a greater NPV, project B will be selected.
Q2c) Project A lasts for 2 years whereas project B lasts for 3 years. The minimum common multiplier of the different duration is 6 years. Therefore the adjusted NPV with a duration of 6 years, which the project A is repeated by 3 times and project B is repeated by 2 times, is calculated. The adjusted NPVs for project A and project B are 330.7 and 253.6 respectively. With a greater adjusted NPV, project A will be selected.

## Q3
Q3a)
|  |  |  | FS = 3 |  |  | FS=1
| 0 | A | 2 | 5 | B | 7 | 8 | C | 10
| 4 |  |  | 1 |  |  | 0
| 4 | 2 | 6 | 6 | 2 | 8 | 8 | 2 | 10
Q3b) |  |  |  | FS = 3 |  |  | FS = 1
| 0 | A | 2 | 2 | B | 7 | 7 | C | 10
| 0 |  |  | 0 |  |  | 0
| 0 | 2 | 2 | 2 | 5 | 7 | 7 | 3 | 10
Q3c)

## Q4
Q4a）
| Activity | Cost percentage | Cost | Activity | Cost percentage | Cost
Router systems project cost | Definition | 10% | 60000 | Objectives | 4% | 24000
|  |  |  | Requirements | 6% | 36000
| Design | 40% | 240000 | Inputs | 3% | 18000
|  |  |  | Outputs | 3% | 18000
|  |  |  | Files | 4% | 24000
|  |  |  | Interfaces | 10% | 60000
|  |  |  | Programming | 20% | 120000
| Implementation | 50% | 300000 | In-house testing | 40% | 240000
|  |  |  | Customer testing & Review | 10% | 60000
Total cost | 600000
Q4a) The estimated costs are $240,000 for Design, $120,000 for Programming and $240,000 for In-house testing.
Q4b)