## Q1
0 | A | 7 |  |  |  |  | 12 | D | 31 | 21 | F | 28
0 | Start story draft using template | [5 empty] | 0 | Coordinate needs proposal with client |  | 3 | Draft future plans for client company
0 | 7 | 7 |  | 7 | C | 12 | 12 | 19 | 31 | 24 | 7 | 31
|  |  |  | 0 | Create“due diligence” rough draft
|  |  |  | 7 | 5 | 12
0 | B | 4 |  |  |  |  | 12 | E | 21 | 31 | H | 36 | 28 | I | 36
3 | Research client firm | [5 empty] | 3 | Estimate future demand and cash flows |  | 0 | Integrate all drafts into first-draft proposal |  | 5 | Line up potential sources of capital
3 | 4 | 7 |  |  |  |  | 15 | 9 | 24 | 31 | 5 | 36 | 33 | 8 | 41
[16 empty] | 41 | K | 70
[16 empty] | 0 | Sign contracts and transfer funds
[16 empty] | 41 | 29 | 70
[7 empty] | 12 | G | 22 |  |  |  | 36 | J | 41
[7 empty] | 9 | Create and approve legal documents |  |  |  |  | 0 | Check, approve, and print final legal proposal
[7 empty] | 21 | 10 | 31 |  |  |  | 36 | 5 | 41
Time in Workdays
Activity | Optimistic | Most likely | Pessimistic | te | Variance
A | 4 | 7 | 10 | 7 | 1
B | 2 | 4 | 6 | 4 | 0.44444
C | 2 | 5 | 8 | 5 | 1
D | 16 | 19 | 22 | 19 | 1
E | 6 | 9 | 12 | 9 | 1
F | 1 | 7 | 13 | 7 | 4
G | 4 | 10 | 16 | 10 | 4
H | 2 | 5 | 8 | 5 | 1
I | 5 | 8 | 11 | 8 | 1
J | 2 | 5 | 8 | 5 | 1
K | 17 | 29 | 41 | 29 | 16
b) | Path | te | variance | sd
| ACDHJK | 70 | 21 | 4.5826
| z = | 0 | =(t_s-t_e)/sd
| prob = | 50%
c) | If the project must meet the 70-day requirement with 95 percent chance, what would the expected project duration have to be?
| prob = | 95%
| t_s = | 70
We need to calculate the expected duration of the project (t_e)
| z = | 1.6449
| t_e = | 62.4623
We need the project duration to be 62.5 days.

## Q2
Activity | Duration | Predecessor(s) | Required machines |  | When the required resources exceed the available resources, the heuristic procedure that is based on a priority below
A | 2 | None | 2 |  | - Minimum slack
B | 2 | A | 1 |  | - Smallest duration
C | 3 | A | 2 |  | - Lowest activity identification number
D | 1 | A | 2
E | 1 | D | 1
F | 1 | B, C, E | 3
Initial resource allocation
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | [5 empty] | 2 | B | 4
A | 2 | 2 | [9 empty] | 1
B |  |  | 1 | 1 | [7 empty] | 3 | 2 | 5
C |  |  | 2 | 2 | 2
D |  |  | 2
E |  |  |  | 1
F | [5 empty] | 3 |  |  | 0 | A | 2 | 2 | C | 5 |  |  |  | 5 | F | 6
Total requirment | 2 | 2 | 5 | 4 | 2 | 3 |  |  | 0 |  |  | 0 | [5 empty] | 0
|  |  | Exceed | Exceed |  |  |  |  | 0 | 2 | 2 | 2 | 3 | 5 |  |  |  | 5 | 1 | 6
Move B to week 5, then F has to be moved to week 7
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
A | 2 | 2 | [9 empty] | 2 | D | 3 | 3 | E | 4
B |  |  |  |  | 1 | 1 | [5 empty] | 1 |  |  | 1
C |  |  | 2 | 2 | 2 | [6 empty] | 3 | 1 | 4 | 4 | 1 | 5
D |  |  | 2
E |  |  |  | 1
F | [6 empty] | 3 |  | 1. Minimum slack -> move B,D,E
Total requirment | 2 | 2 | 4 | 3 | 3 | 1 | 3 |  | 2. Smallest duration -> move B
Exceed
Move D week 6, then E has to move to week 7 and F has to move to week 8
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
A | 2 | 2
B |  |  |  |  | 1 | 1
C |  |  | 2 | 2 | 2
D | [5 empty] | 2
E | [6 empty] | 1
F | [7 empty] | 3
Total requirment | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3
b) Optimal solution
Activity | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
A | 2 | 2
B |  |  | 1 | 1
C |  |  |  | 2 | 2 | 2
D |  |  | 2
E |  |  |  |  | 1
F | [6 empty] | 1
Total requirment | 2 | 2 | 3 | 3 | 3 | 2 | 1