## Sheet1
Crashing | [7 empty] | Normal Cost | Crash Cost | Allowable Crash Time | Slope
Task | Description | Optimistic | Likely | Pessimistic | Mean | Variance | Predecessor | (in $000) | (in $000) | (Week) | ($000/week)
A | Soil |  |  |  | 0 | 0 |  |  |  |  | N/A
B | Walkways |  |  |  | 0 | 0 |  |  |  |  | #DIV/0!
C | Irrigation |  |  |  | 0 | 0 |  |  |  |  | #DIV/0!
D | Fence |  |  |  | 0 | 0 |  |  |  |  | #DIV/0!
E | Lighting |  |  |  | 0 | 0 |  |  |  |  | #DIV/0!
F | Planting |  |  |  | 0 | 0 |  |  |  |  | #DIV/0!
Duration
| Critical Path | ACEFIJ
| Variance | 0
| StDev | 0
Z-score
| Pro(T<=28) | 50%
| Total Cost | #REF!
| Expected cost of being late | 0
| Grand Total | #REF!
Task ID | Description | Duration | Predecessor | Required Staff | Normal Cost | Slope | Allowable Reduction
A | Soil | 2 | None | 2 | 500 | N/A | None
B | Walkways | 2 | A+FS2 | 2 | 800 | $100/week | 1
C | Irrigation | 3 | A | 1 | 800 | $200/week | 1
D | Fence | 3 | A | 1 | 600 | $120/week | 1
E | Lighting | 3 | B, C+FS2 | 2 | 400 | $150/week | 1
F | Planting | 1 | D, E | 2 | 300 | N/A | None
Task ID | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
A | 2 | 2
B |  |  |  |  | 2 | 2
C |  |  | 1 | 1 | 1
D | [5 empty] | 1 | 1 | 1
E | [7 empty] | 2 | 2 | 2
F | [10 empty] | 1
Total | 2 | 2 | 1 | 1 | 3 | 3 | 1 | 3 | 2
Limit | 3S | 3S | 3S | 3S | 3S | 3S | 3S | 3S | 3S
i1
path | duration | E | C | b
ABEF | 10 | 9 | 9 | 8
ACEF | 11 | 10 | 9
ADF | 6 | 6 | 6
cost | 3400 | 3550 | 3750
indirect | 3080 | 2800 | 2520
total | 6480 | 6350 | 6270
Task | % Complete | EV | AC | PV | CV | SV
1 | Finished | 6 | 5 | 6 | 1 | 0 |  | SPI | CPI
2 | 50% | 20 | 8 | 20 | 12 | 0 |  | 1.2258 | 2.1714
3 | 60% | 30 | 12 | 21 | 18 | 9
4 | 70% | 20 | 10 | 15 | 10 | 5
Cumulative Totals |  | 76 | 35 | 62 | 41 | 14
0.57143
1 | 6 | 5 | 6
2 | 20 | 8 | 20
3 | 30 | 12 | 21
4 | 20 | 10 | 15
| 76 | 35 | 62
Task | % Complete | EV | AC | PV | CV | SV
1 | Finished | 6 | 5 | 6 | 1 | 0 |  | SPI | CPI
2 | 50% | 20 | 10 | 20 | 10 | 0 |  | 1.0411 | 1.6522
3 | 60% | 30 | 16 | 27 | 14 | 3
4 | 70% | 20 | 15 | 20 | 5 | 0
Cumulative Totals |  | 76 | 46 | 73 | 30 | 3
Task | % Complete | EV | AC | PV | CV | SV
1 | Finished | 6 | 5 | 6 | 1 | 0 |  | SPI | CPI
2 | Finished | 20 | 14 | 20 | 6 | 0 |  | 1.2941 | 1.746
3 | Finished | 30 | 20 | 30 | 10 | 0
4 | Finished | 20 | 15 | 20 | 5 | 0
5 | 0% | 16 | 0 | 0 | 16 | 16
6 | 50% | 18 | 9 | 9 | 9 | 9
|  | 110 | 63 | 85 | 47 | 25
12