## Q1a (hidden)
Q1a
| ES | Code | EF
| TS | Activity Name
| LS | Duration | LF | [5 empty] | 10 | G | 16
[9 empty] | 4 | Documentation
[5 empty] | 3 | B | 10 |  | 14 | 6 | 20 | 16 | H | 18
[5 empty] | 4 | Marketing assessment | [5 empty] | 4 | Pricing
[5 empty] | 7 | 7 | 14 |  |  |  |  | 20 | 2 | 22
| 0 | A | 3
| 0 | Requirement | [6 empty] | 9 | D | 16 |  |  |  | 22 | I | 26 | 26 | J | 29
| 0 | 3 | 3 | [5 empty] | 1 | Development |  |  |  |  | 0 | Production |  | 0 | Distribtuion
[9 empty] | 10 | 7 | 17 |  |  |  | 22 | 4 | 26 | 26 | 3 | 29
[5 empty] | 3 | C | 9 |  |  |  |  | 17 | F | 22
[5 empty] | 0 | Design | [5 empty] | 0 | Revising
[5 empty] | 3 | 6 | 9 |  |  |  |  | 17 | 5 | 22
[9 empty] | 9 | E | 17
[9 empty] | 0 | Testing
[9 empty] | 9 | 8 | 17
| Cost estimates |  |  | Time estimates
| Task | Normal Cost ($000) |  | Task | Optimistic | Likely | Pessimistic | Expected duration | Variance
| A | 10 |  | A | 2 | 3 | 4 | 3 | 0.11111
| B | 20 |  | B | 4 | 7 | 10 | 7 | 1
| C | 15 |  | C | 5 | 6 | 7 | 6 | 0.11111
| D | 45 |  | D | 6 | 7 | 8 | 7 | 0.11111
| E | 10 |  | E | 6 | 8 | 10 | 8 | 0.44444
| F | 15 |  | F | 4 | 5 | 6 | 5 | 0.11111
| G | 20 |  | G | 3 | 6 | 9 | 6 | 1
| H | 10 |  | H | 2 | 2 | 2 | 2 | 0
| I | 5 |  | I | 3 | 4 | 5 | 4 | 0.11111
| J | 35 |  | J | 2 | 3 | 4 | 3 | 0.11111
| Total cost | 185
Expected time = (optimistic + 4*(likely)+pessimistic)/6
Variance = ((pessimistic - optimistic)/6))^2
z = (specified time - expected duration)/ path standard time
probability of project completing in 28 week = NORMSDIST(z)
| Path | Expected duration | Variance | Standard deviation
| ABGHIJ | 25 | 2.3333 | 1.5275
| ACDFIJ | 28 | 0.66667 | 0.8165
| ACEFIJ | 29 | 1 | 1 | Expected critical path
| z | -1
| Probability | 15.87%
Q1a)
What is the estimated completion time for the project?
Under the "Normal" circustance, the estimated completion time for the project is 29 weeks.
What is the estimated project budget?
The estimated project budget is $185,000.
What is the probability that the project can be completed in 28 week?
The critical path is ACEFIJ with an expected duration of 29 weeks and a path variance of 1 week. The z score is calculated by (28-29)/ 1 = -1. The probability that the project can be completed in 28 weeks is 15.9%, which is the probabiltiy of a test statistic being sameller than -1 in a normal distribution.

## Q1b (hidden)
Q1b
| Task | Normal Cost ($000) | Crash cost ($000) | Allowable decrease (Week) | Slope
| A | 10 | 10 | 0 | n/a
| B | 20 | 25 | 1 | 5
| C | 15 | 30 | 1 | 15
| D | 45 | 50 | 1 | 5
| E | 10 | 16 | 1 | 6
| F | 15 | 18 | 1 | 3
| G | 20 | 30 | 2 | 5
| H | 10 | 15 | 1 | 5
| I | 5 | 5 | 0 | n/a
| J | 35 | 55 | 1 | 20
Step 0: Draw project network and find critical path
[6 empty] | G |  | H |  |  |  |  | Path | Duration
[6 empty] | 6 |  | 2 |  |  |  |  | ABGHIJ | 25
|  |  |  | B | [8 empty] | ACDFIJ | 28
|  |  |  | 7 | [8 empty] | ACEFIJ | 29 | Critical path
|  | A | [7 empty] | I |  | J | Duration | Normal cost ($000) | Overdue cost ($000) | Total cost ($000)
|  | 3 |  |  |  | D |  |  |  | 4 |  | 3 | 29 | 185 | 30 | 215
|  |  |  | C |  | 7 |  | F
|  |  |  | 6 |  |  |  | 5
E
8
Step 1: Reduce task F for one week (because F has the smallest slope )
Cost
| Crash F | 3
[6 empty] | G |  | H |  |  |  |  | Path | Duration
[6 empty] | 6 |  | 2 |  |  |  |  | ABGHIJ | 25
|  |  |  | B | [8 empty] | ACDFIJ | 27
|  |  |  | 7 | [8 empty] | ACEFIJ | 28 | Critical path
|  | A | [7 empty] | I |  | J | Duration | Cost | Overdue cost ($000) | Total cost ($000)
|  | 3 |  |  |  | D |  |  |  | 4 |  | 3 | 28 | 188 | 0 | 188
|  |  |  | C |  | 7 |  | F
|  |  |  | 6 |  |  |  | 4
[6 empty] | E |  | (x)
8
Step 2: Crash task E for one week
| 3 options: | Cost
| 1. Crash C | 15
| 2. Crash E | 6 |  |  |  | G |  | H |  |  |  |  | Path | Duration
| 3. Crash J | 20 |  |  |  | 6 |  | 2 |  |  |  |  | ABGHIJ | 25
|  |  |  | B | [8 empty] | ACDFIJ | 27 | Critical path
|  |  |  | 7 | [8 empty] | ACEFIJ | 27 | Critical path
|  | A | [7 empty] | I |  | J | Duration | Cost | Overdue cost ($000) | Total cost ($000)
|  | 3 |  |  |  | D |  |  |  | 4 |  | 3 | 27 | 194 | 0 | 194
|  |  |  | C |  | 7 |  | F
|  |  |  | 6 |  |  |  | 4
E
7
(x)
Step 3: Crash task C for one week
| 2 options: | Cost
| 1. Crash C | 15
| 2. Crash J | 20 |  |  |  | G |  | H |  |  |  |  | Path | Duration
[6 empty] | 6 |  | 2 |  |  |  |  | ABGHIJ | 25
|  |  |  | B | [8 empty] | ACDFIJ | 26 | Critical path
|  |  |  | 7 | [8 empty] | ACEFIJ | 26 | Critical path
|  | A | [7 empty] | I |  | J | Duration | Cost | Overdue cost ($000) | Total cost ($000)
|  | 3 |  |  |  | D |  |  |  | 4 |  | 3 | 26 | 209 | 0 | 209
|  |  |  | C |  | 7 |  | F
|  |  |  | 5 |  |  |  | 4
|  |  |  | (x) |  | E
7
Step 4: Crash task J for one week
Cost
| 1. Crash J | 20
[6 empty] | G |  | H |  |  |  |  | Path | Duration
[6 empty] | 6 |  | 2 |  |  |  |  | ABGHIJ | 24
|  |  |  | B | [8 empty] | ACDFIJ | 25 | Critical path
|  |  |  | 7 | [8 empty] | ACEFIJ | 25 | Critical path
|  | A | [7 empty] | I |  | J | Duration | Cost | Overdue cost ($000) | Total cost ($000)
|  | 3 |  |  |  | D |  |  |  | 4 |  | 2 | 25 | 229 | 0 | 229
|  |  |  | C |  | 7 |  | F
|  |  |  | 5 |  |  |  | 4
E
7
| Crashing summary |  |  |  |  | Time estimates
| Task to crash | Duration | Cost ($000) |  |  | Task | Optimistic | Likely | Pessimistic | Expected duration | Variance
|  | 29 | 215 |  |  | A | 2 | 3 | 4 | 3 | 0.11111
| F | 28 | 188 | optimal |  | B | 4 | 7 | 10 | 7 | 1
| E | 27 | 194 |  |  | C | 5 | 6 | 7 | 6 | 0.11111
| C | 26 | 209 |  |  | D | 6 | 7 | 8 | 7 | 0.11111
| J | 25 | 229 |  |  | E | 6 | 8 | 10 | 8 | 0.44444
[6 empty] | F | 3 | 4 | 5 | 4 | 0.11111 | Crashed
[6 empty] | G | 3 | 6 | 9 | 6 | 1
[6 empty] | H | 2 | 2 | 2 | 2 | 0
[6 empty] | I | 3 | 4 | 5 | 4 | 0.11111
[6 empty] | J | 2 | 3 | 4 | 3 | 0.11111
Expected time = (optimistic + 4*(likely)+pessimistic)/6
Variance = ((pessimistic - optimistic)/6))^2
z = (t_s-t_e)/sd
probability of project completing in 28 week = NORMSDIST(z)
| Path | Expected duration | Variance | Standard deviation
| ABGHIJ | 25 | 2.3333 | 1.5275
| ACDFIJ | 27 | 0.66667 | 0.8165
| ACEFIJ | 28 | 1 | 1 | Expected critical path
| z | 0
| Probability | 50%
Q1b)
Which tasks do you recommend for crashing?
The optimal crashing plan is to crash task F for one week. The duration of the project will be reduced to 28 weeks and the toal cost is $188,000.
What is the probability of completing the project in 28 weeks?
The critical path is ACEFIJ with an expected duration of 28 weeks and a variance of 1 week. The probability that the project can be completed in 28 weeks is 50%, which is the probability of test statistic being smaller than 0 in a normal distribution.

## Q1
Details of B&W Projects
[8 empty] | Normal Cost | Crash Cost | Allowable Crash Time | Slope
Task | Description | Optimistic | Likely | Pessimistic | Mean | Variance | Predecessor | (in $000) | (in $000) | (Week) | ($000/week)
A | Requirement | 2 | 3 | 4 | 3 | 0.11111 | None | 10 | 10 | 0 | N/A
B | Market assessment | 4 | 7 | 10 | 7 | 1 | A | 20 | 25 | 1 | 5
C | Design | 5 | 6 | 7 | 6 | 0.11111 | A | 15 | 30 | 1 | 15
D | Development | 6 | 7 | 8 | 7 | 0.11111 | C | 45 | 50 | 1 | 5
E | Testing | 6 | 8 | 10 | 8 | 0.44444 | C | 10 | 16 | 1 | 6
F | Revising | 4 | 5 | 6 | 5 | 0.11111 | D, E | 15 | 18 | 1 | 3
G | Documentation | 3 | 6 | 9 | 6 | 1 | B | 20 | 30 | 2 | 5
H | Pricing | 2 | 2 | 2 | 2 | 0 | G | 10 | 15 | 1 | 5 |  | Cost of Late
I | Production | 3 | 4 | 5 | 4 | 0.11111 | F, H | 5 | 5 | 0 | N/A |  | 30000
J | Distribution | 2 | 3 | 4 | 3 | 0.11111 | I | 35 | 55 | 1 | 20
185
Network (Normal Circustance, also Iteration 1 of crashing)
| 0 | A | 3 |  | 3 | B | 10 |  | 10 | G | 16 |  | 16 | H | 18 | 22 | I | 26 | 26 | J | 29
| 0 | Requirement |  |  | 4 | Market assessment |  |  | 4 | Documentation |  |  | 4 | Pricing |  | 0 | Production |  | 0 | Distribution
| 0 | 3 | 3 |  | 7 | 7 | 14 |  | 14 | 6 | 20 |  | 20 | 2 | 22 | 22 | 4 | 26 | 26 | 3 | 29
| Duration | 29 |  |  | 3 | C | 9 |  | 9 | D | 16 |  | 17 | F | 22
| Critical Path | ACEFIJ |  |  | 0 | Design |  |  | 1 | Development |  |  | 0 | Revising
| Variance | 1 |  |  | 3 | 6 | 9 |  | 10 | 7 | 17 |  | 17 | 5 | 22
| StDev | 1
| Z-score | -1
| Pro(T<=28) | 15.87% | 84.13% | [5 empty] | 9 | E | 17
[9 empty] | 0 | Testing
| Total Cost | 185000 | [6 empty] | 9 | 8 | 17
| Expected cost of being late | 25240.3424
| Grand Total | 210240.3424
Iteration 2 (After crashing F)
| 0 | A | 3 |  | 3 | B | 10 |  | 10 | G | 16 |  | 16 | H | 18 | 21 | I | 25 | 25 | J | 28
| 0 | Requirement |  |  | 3 | Market assessment |  |  | 3 | Documentation |  |  | 3 | Pricing |  | 0 | Production |  | 0 | Distribution
| 0 | 3 | 3 |  | 6 | 7 | 13 |  | 13 | 6 | 19 |  | 19 | 2 | 21 | 21 | 4 | 25 | 25 | 3 | 28
| Duration | 28 |  |  | 3 | C | 9 |  | 9 | D | 16 |  | 17 | F | 21
| Critical Path | ACEFIJ |  |  | 0 | Design |  |  | 1 | Development |  |  | 0 | Revising
| Variance | 1 |  |  | 3 | 6 | 9 |  | 10 | 7 | 17 |  | 17 | 4 | 21
| StDev | 1
| Z-score | 0
| Pro(T<=28) | 50% | 50% | [5 empty] | 9 | E | 17
[9 empty] | 0 | Testing
| Total Cost | 188000 | [6 empty] | 9 | 8 | 17
| Expected cost of being late | 15000
| Grand Total | 203000
Iteration 3 (After crashing F and E)
| 0 | A | 3 |  | 3 | B | 10 |  | 10 | G | 16 |  | 16 | H | 18 | 20 | I | 24 | 24 | J | 27
| 0 | Requirement |  |  | 2 | Market assessment |  |  | 2 | Documentation |  |  | 2 | Pricing |  | 0 | Production |  | 0 | Distribution
| 0 | 3 | 3 |  | 5 | 7 | 12 |  | 12 | 6 | 18 |  | 18 | 2 | 20 | 20 | 4 | 24 | 24 | 3 | 27
| Duration | 27 |  |  | 3 | C | 9 |  | 9 | D | 16 |  | 16 | F | 20
| Critical Path | ACEFIJ |  |  | 0 | Design |  |  | 0 | Development |  |  | 0 | Revising
| Variance | 1 |  |  | 3 | 6 | 9 |  | 9 | 7 | 16 |  | 16 | 4 | 20
| StDev | 1
| Z-score | 1
| Pro(T<=28) | 84.13% | 15.87% | [5 empty] | 9 | E | 16
[9 empty] | 0 | Testing
| Total Cost | 194000 | [6 empty] | 9 | 7 | 16
| Expected cost of being late | 4759.6576
| Grand Total | 198759.6576
Iteration 4 (After crashing F, E, and C)
| 0 | A | 3 |  | 3 | B | 10 |  | 10 | G | 16 |  | 16 | H | 18 | 19 | I | 23 | 23 | J | 26
| 0 | Requirement |  |  | 1 | Market assessment |  |  | 1 | Documentation |  |  | 1 | Pricing |  | 0 | Production |  | 0 | Distribution
| 0 | 3 | 3 |  | 4 | 7 | 11 |  | 11 | 6 | 17 |  | 17 | 2 | 19 | 19 | 4 | 23 | 23 | 3 | 26
| Duration | 26 |  |  | 3 | C | 8 |  | 8 | D | 15 |  | 15 | F | 19
| Critical Path | ACEFIJ and ACDFIJ |  |  | 0 | Design |  |  | 0 | Development |  |  | 0 | Revising
| Variance | 1 |  |  | 3 | 5 | 8 |  | 8 | 7 | 15 |  | 15 | 4 | 19
| StDev | 1
| Z-score | 2
| Pro(T<=28) | 97.72% | 2.275% | [5 empty] | 8 | E | 15
[9 empty] | 0 | Testing
| Total Cost | 209000 | [6 empty] | 8 | 7 | 15
| Expected cost of being late | 682.504
| Grand Total | 209682.504
Iteration 5 (After crashing F, E, C and J)
| 0 | A | 3 |  | 3 | B | 10 |  | 10 | G | 16 |  | 16 | H | 18 | 19 | I | 23 | 23 | J | 25
| 0 | Requirement |  |  | 1 | Market assessment |  |  | 1 | Documentation |  |  | 1 | Pricing |  | 0 | Production |  | 0 | Distribution
| 0 | 3 | 3 |  | 4 | 7 | 11 |  | 11 | 6 | 17 |  | 17 | 2 | 19 | 19 | 4 | 23 | 23 | 2 | 25
| Duration | 25 |  |  | 3 | C | 8 |  | 8 | D | 15 |  | 15 | F | 19
| Critical Path | ACEFIJ and ACDFIJ |  |  | 0 | Design |  |  | 0 | Development |  |  | 0 | Revising
| Variance | 1 |  |  | 3 | 5 | 8 |  | 8 | 7 | 15 |  | 15 | 4 | 19
| StDev | 1
| Z-score | 3
| Pro(T<=28) | 99.87% | 0.135% | [5 empty] | 8 | E | 15
[9 empty] | 0 | Testing
| Total Cost | 229000 | [6 empty] | 8 | 7 | 15
| Expected cost of being late | 40.4969
| Grand Total | 229040.4969
Table of Summary
[10 empty] | Expected Cost of |  | Crashed
[8 empty] | Duration | Direct Cost | being late to market | Total | Activity | Pro(T<=28)
[8 empty] | 29 | 185000 | 25240.3424 | 210240.3424 | N/A | 15.87%
[8 empty] | 28 | 188000 | 15000 | 203000 | F | 50%
[8 empty] | 27 | 194000 | 4759.6576 | 198759.6576 | E | 84.13%
[8 empty] | 26 | 209000 | 682.504 | 209682.504 | C | 97.72%
[8 empty] | 25 | 229000 | 40.4969 | 229040.4969 | J | 99.87%
- Using the information of a, m, and c, we compute the average duration and variance.
- We combine both Tables 1 and 2 and then create the new column "Slope".
Q1a) Under "normal" condition, the project budget is $185,000 and the project duration is 29 weeks. The probability of being late to the market is 84.1%.
The activity to crash in Iteration 1 is F (Revising).
The activity to crash in Iteration 3 is C (Design).
The activity to crash in Iteration 2 is E (Revising).
The activity to crash in Iteration 4 is J (Distribution) because crashing D alone (at this moment, E cannot be crashed any more) won't reduce the expected project duration.
There are two critical paths: but path ACEFIJ has a larger variance and is chosen for subsequent analysis.
The expected project duration cannot be reduced any further.
As the Table of Summary indicated, the optimal plan is to crash activities F and E. Under such plan, the probability of completing the project on time is 84.1% and the total expected cost is $197,173.

## Q2
Q2a
| Year | Project A | Project B
| 0 | -500 | -500
| 1 | 400 | 300
| 2 | 300 | 350
| 3 | n/a | 80
| IRR | 27.18% | 25.77%
Q2b | Discount Rate | 8%
NPV = Initial investment + NPV(Discount rate, cells of future cash flow)
|  | Project A | Project B
| NPV | 127.572 | 141.3529
Q2c |  | Duration
| Project A | 2 | years
| Project B | 3 | years
| Minimum common multiplier |  | 6
| Year | Project A |  |  | Project B
|  | Inflow | Outflow | Cummulative cash flow | Inflow | Outflow | Cummulative cash flow
| 0 |  | -500 |  |  | -500
| 1 | 400 |  | 400 | 300 |  | 300
| 2 | 300 | -500 | -200 | 350 |  | 350
| 3 | 400 |  | 400 | 80 | -500 | -420
| 4 | 300 | -500 | -200 | 300 |  | 300
| 5 | 400 |  | 400 | 350 |  | 350
| 6 | 300 |  | 300 | 80 |  | 80
|  |  | adjusted NPV | 330.7137 |  | adjusted NPV | 253.5635
| Discount Rate | 8%
NPV = Initial investment + NPV(Discount rate, cells of future cash flow)
Q2d
| Year | Project A | ACF_t/(1+IRR)^t
| 0 | -500
| 1 | 300 | 235.8899
| 2 | 350 | 216.3935
| 3 | 80 | 38.8915
| IRR | 27.18%
| adjusted initial investment | 491.1749
| IRR reduction | 8.8251
Q2a) The IRR for project A is 27.2% while the IRR for project B is 25.8%.
Q2b) Without considering unequal project duration, the NPV for project A is 127.6 while the NPV project B is 141.4. With a greater NPV, project B will be selected.
Q2c) Project A lasts for 2 years whereas project B lasts for 3 years. The minimum common multiplier of the different duration is 6 years. Therefore the adjusted NPV with a duration of 6 years, which the project A is repeated by 3 times and project B is repeated by 2 times, is calculated. The adjusted NPVs for project A and project B are 330.7 and 253.6 respectively. With a greater adjusted NPV, project A will be selected.
0 =−𝐼_0+∑_𝑡=1^𝑇▒𝐴𝐶𝐹_𝑡/(1+𝐼𝑅𝑅)^𝑡
𝐼_0=∑_𝑡=1^𝑇▒𝐴𝐶𝐹_𝑡/(1+𝐼𝑅𝑅)^𝑡
The initial cash outflow should be reduced by 8.8 to 491.2 to assure that both projects have the same IRR.

## Q3
Q3a)
| 0 | A | 2 | Lag 3 | 5 | B | 7 | Lag 1 | 8 | C | 10
| 0 |  |  |  | 0 |  |  |  | 0
| 0 | 2 | 2 |  | 5 | 2 | 7 |  | 8 | 2 | 10
Q3b)
| 0 | A | 2 | Lag 3 | 2 | B | 7 | Lag 1 | 7 | C | 10
| 0 |  |  |  | 0 |  |  |  | 0
| 0 | 2 | 2 |  | 2 | 5 | 7 |  | 7 | 3 | 10
Q3c) The completion time for tasks with FS lag and the overall completion time of the project remain the same for both approaches. However, adding the FS lag to the duration of subsequent activity can lead to inconsistency of resourse (time) assignment on subsequent activity. This can cause problem when performing resource leveling, especially when time is limited.

## Q4
Q4a）
| Activity | Cost percentage | Cost | Activity | Cost percentage | Cost
Router systems project cost | Definition | 10% | 60000 | Objectives | 4% | 24000
|  |  |  | Requirements | 6% | 36000
| Design | 40% | 240000 | Inputs | 3% | 18000
|  |  |  | Outputs | 3% | 18000
|  |  |  | Files | 4% | 24000
|  |  |  | Interfaces | 10% | 60000
|  |  |  | Programming | 20% | 120000
| Implementation | 50% | 300000 | In-house testing | 40% | 240000
|  |  |  | Customer testing & Review | 10% | 60000
[5 empty] | Total | 600000
Total cost | 600000
Q4a) The estimated costs are $240,000 for Design, $120,000 for Programming and $240,000 for In-house testing.
Q4b) What weaknesses are inherent in this estimating approach?
This apportion method is a top-bottom budgetting procedure. With this approach, estimates are usually made by top managers who may not be familiar with the processes used to compete the project. This leads to relatively low accuracies and high uncertainties of estimates compared to a bottom-top approach. Moreover, it has also been a challenge to come up with the total cost and the weights of subsequent tasks. When the total cost and weights of tasks being estimated by experience and historical data, project can fail due to uniqueness of different projects.